## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Introduction to Project | MUST HAVE | No Dependency | Aneesh | 3 - Completed
Sprint 2 | Sprint 2 | US-2 | Workflow Creation and Project Goal Definition | MUST HAVE | Lucidchart | Aneesh | 3 - Completed
Sprint 3 | Sprint 3 | US-3 | Collect customer reviews from multiple platforms to centralize raw feedback data. | MUST HAVE | Different Scrapers | Aneesh,Santhosh | 3 - Completed
Sprint 4 | Sprint 4 | US-4 | Clean and preprocess raw review data to remove noise and normalize text. | SHOULD HAVE | OpenAI,Groq Embeddings | Aneesh | 3 - Completed
Sprint 5 | Sprint 5 | US-5 | Database Design (FAISS Schema and Embedding Collection Setup) | MUST HAVE | FAISS | Aneesh | 3 - Completed
Sprint 6 | Sprint 6 | US-6 | Implement a LangChain retriever to fetch contextually relevant reviews based on user queries. | SHOULD HAVE | Langchain | Aneesh | 3 - Completed
Sprint 7 | Sprint 7 | US-7 | Content Gap Detection and Improvement Module | MUST HAVE | Tracker, Usage Logs | Aneesh | 3 - Completed
Sprint 8 | Sprint 8 | US-8 | UI Integration and Query Flow Implementation | MUST HAVE | Streamlit, Recommendation Engine | Aneesh | 3 - Completed
Sprint 9 | Sprint 9 | US-9 | Final Testing and System Integration with Powerpoint and Demo Preparation | MUST HAVE | All previous modules | Aneesh,Preethi,Gaythri | 3 - Completed
Sprint 10 | Sprint 10 | US-10 | System Deployment (Cloud/Local), CI/CD Setup, Performance Optimization | MUST HAVE | Entire system | Aneesh | 3- Completed
Sprint 11 | Sprint 11 | US-11 | Full Documentation (Tech Docs, Architecture, API, UI Flow) & User Training | SHOULD HAVE | All previous modules | Entire Team | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 118 | 42 | 39 | 26 | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US_1 | 1 | Project Setup and Repository Initialization | 2025-12-29 | 2025-12-30 | Aneesh | Planning | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_2 | 2 | Workflow Definition and Requirement Finalization | 2025-12-31 | 2026-01-01 | Aneesh | Design | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_3 | 3 | Architecture Diagram and Module Design | 2026-01-02 | 2026-01-04 | Aneesh | Design | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_4 | 4 | Web Scraping Module Development | 2026-01-05 | 2026-01-07 | Aneesh | Build | Completed | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_5 | 5 | Data Cleaning and Preprocessing Pipeline | 2026-01-08 | 2026-01-10 | Aneesh | Build | Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_6 | 6 | Sentiment and Aspect Tagging Module | 2026-01-11 | 2026-01-13 | Aneesh | Build | Completed | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_7 | 7 | Embedding Generation using Sentence Transformers | 2026-01-14 | 2026-01-15 | Aneesh | Build | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_8 | 8 | FAISS Vector Database Setup and Indexing | 2026-01-16 | 2026-01-18 | Aneesh | Build | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_9 | 9 | LangChain Retriever Integration | 2026-01-19 | 2026-01-21 | Aneesh | Integration | Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_10 | 10 | RAG Pipeline with Groq LLM Integration | 2026-01-22 | 2026-01-25 | Aneesh | Integration | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_11 | 11 | Streamlit Multi-Page UI Development and Deployment | 2026-01-26 | 2026-01-27 | Aneesh | Deployment | Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_ID | 12 | System Testing, Debugging & Performance Fixes | 2026-01-28 | 2026-02-02 | Aneesh | Test | Completed | 15 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_ID | 13 | Final Demo Preparation & Presentation Building | 2026-02-03 | 2026-02-10 | Aneesh,Preethi,Gaythri | Others | Completed | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_ID | 14 | Documentation (Technical + User Manual) | 2026-02-11 | 2026-02-16 | Aneesh | Documentation | Completed | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_ID | 15 | Project Closure, Review & Submission | 2026-02-17 | 2026-02-19 | Entire Team | Others | Ongoing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Unclear system architecture while defining RAG flow and module interaction | Redesigned architecture diagram and validated end-to-end data flow from scraping to UI.
Sprint 2 | Day 7 | Issues during web scraping due to dynamic loading and rate limits | Implemented request throttling and optimized scraping logic with retry handling.
Sprint 3 | Day 11 | Inconsistent review formats causing preprocessing errors | Standardized text cleaning pipeline and added validation checks.
Sprint 4 | Day 16 | Confusion in designing metadata schema for sentiment and aspect tagging | Redefined metadata structure and aligned tagging format across modules.
Sprint 5 | Day 22 | Embedding generation latency and memory overhead on local machine | Switched to lightweight sentence-transformer model and optimized batch size.
Sprint 6 | Day 24 | FAISS index mismatch with metadata causing retrieval errors | Rebuilt FAISS index and ensured correct index-to-docstore mapping.
Sprint 7 | Day 30 | Groq LLM integration errors due to model version changes | Updated model configuration and validated API integration with fallback handling.
Sprint 8 | Day 36 | Streamlit multi-page navigation conflicts and state reset issues | Refactored session state handling and modularized page routing.
Sprint 9 | Day 40 | Deployment failure due to incompatible torch and Python versions on Streamlit Cloud | Removed heavy torch dependency and replaced embedding logic with lightweight custom function.
Sprint 10 | Day 45 | Missing FAISS store files during cloud deployment | Refactored file paths to use relative directory structure and verified repository inclusion.
Sprint 11 | Day 50 | Final integration bugs between retriever and RAG chain output formatting | Standardized context formatting and added robust error handling in AI assistant module.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-30 | 2026-01-02 | Aneesh | Designing system architecture and defining RAG pipeline modules | Starting implementation without finalized architecture | Structured documentation and modular planning | Finalized end-to-end architecture from scraping to Streamlit UI
2 | Sprint 2 | 2026-01-03 | 2026-01-07 | Aneesh,Santhosh | Building web scraping pipeline for review collection | Manual data cleaning without automation | Improving preprocessing consistency | Implemented automated scraping and structured data storage
3 | Sprint 3 | 2026-01-08 | 2026-01-12 | Aneesh | Developing text cleaning and preprocessing pipeline | Ignoring inconsistent review formats | Validating processed dataset samples | Standardized normalization and noise removal logic
4 | Sprint 4 | 2026-01-13 | 2026-01-17 | Aneesh | Implementing sentiment and aspect tagging module | Hardcoding tagging rules without flexibility | Testing tagging outputs iteratively | Built structured tagging pipeline with metadata mapping
5 | Sprint 5 | 2026-01-18 | 2026-01-23 | Aneesh | Generating embeddings and building FAISS vector index | Rebuilding embeddings repeatedly without caching | Optimizing embedding batch processing | Created FAISS index with efficient index-to-doc mapping
6 | Sprint 6 | 2026-01-24 | 2026-01-29 | Aneesh | Integrating LangChain retriever with vector database | Direct LLM querying without retrieval context | Validating similarity search outputs | Connected retriever pipeline and verified Top-K retrieval
7 | Sprint 7 | 2026-01-30 | 2026-02-04 | Aneesh | Building RAG chain with Groq LLM integration | Testing LLM without structured prompts | Refining prompt templates for better responses | Implemented context-aware prompt template with controlled output format
8 | Sprint 8 | 2026-02-05 | 2026-02-09 | Aneesh | Developing multi-page Streamlit UI with AI Assistant | Overcomplicating UI components | Improving session state handling | Structured AI Assistant, Evaluation and Reports page
9 | Sprint 9 | 2026-02-10 | 2026-02-14 | Aneesh | Testing full pipeline integration and fixing retrieval bugs | Ignoring edge cases during semantic search | Running regression tests after fixes | Resolved FAISS loading issues and optimized retrieval accuracy
10 | Sprint 10 | 2026-02-15 | 2026-02-17 | Aneesh | Preparing deployment configuration and dependency cleanup | Keeping heavy unnecessary dependencies | Ensuring environment compatibility | Optimized requirements and resolved Python/torch conflicts
11 | Sprint 11 | 2026-02-18 | 2026-02-19 | Aneesh | Final deployment on Streamlit Cloud and documentation | Hardcoding file paths for local environment | Monitoring deployment logs and fixing errors | Refactored paths to relative directories and completed cloud deployment